## Implementation Tracker
Happy Wallet Bank - Frontend OpenTelemetry End-to-End Implementation Tracker
Scope: React + FastAPI + PostgreSQL + Grafana Alloy + Loki/Tempo/Prometheus + Grafana dashboards. Goal: trace customer journeys with a business correlation ID, technical trace/span IDs, safe logs, metrics, and drill-down dashboards without PII/NPI leakage.
ID | Phase | Area | Priority | User Story / Outcome | Implementation Task | Primary Component / File | Dependencies | Acceptance Criteria | Validation / Test | Status | Notes / Decision | Owner
OBS-001 | Foundation | Cross-cutting | High | As an engineering team, we need one telemetry contract so React, FastAPI, DB spans, Alloy and Grafana use the same identifiers and field names. | Document and freeze identifiers: session_id, correlation_id, trace_id, span_id; define safe attributes and prohibited data. | Telemetry contract / README | None | Contract states: correlation_id = one business activity; trace_id = one distributed technical trace; span_id = one operation; session_id = one authenticated browser session. Prohibited: username, password, JWT, customer_id, account number, masked account number, recipient name, DOB, phone, address, raw SQL, SQL parameters, transfer amount in logs/traces. | Peer review against implementation before coding. | Not Started | Correlation ID is searchable across logs/traces; never a metric label.
OBS-002 | Foundation | Cross-cutting | High | As an operator, I need consistent journey and failure-stage names so dashboards aggregate correctly. | Freeze controlled values for journey.type, journey.stage, outcome, failure.stage and service.name. | Telemetry contract / constants | OBS-001 | Only approved low-cardinality values are used; no dynamic customer/account/payment values become metric labels. | Static review + metrics label audit. | Not Started | Suggested journey types: login, transfer. Suggested outcomes: success, failure.
UI-001 | React Instrumentation | React | High | As an operator, I need each authenticated browser session grouped without exposing customer identity. | Generate an opaque session_id after successful login; keep it for the browser session; clear it on logout. | Login.tsx / auth state / session helper | OBS-001 | Login success creates a random opaque session_id; logout removes it; no customer_id/username is used for telemetry grouping. | Login -> inspect session storage; logout -> confirm removal. | Not Started | Use an opaque random ID, not a customer identifier.
UI-002 | React Instrumentation | React | High | As support, I need each login attempt to be independently searchable. | Generate a login correlation_id immediately before the login request and attach it to the login API request. | Login.tsx / apiClient.ts | OBS-001, UI-001 | Every login attempt gets a new correlation_id; retry gets a new login correlation_id; credentials are never logged. | Perform two login attempts and verify two different correlation IDs. | Not Started
UI-003 | React Instrumentation | React | High | As support, I need one transfer correlation_id to cover recipient verification through final payment result. | Create transfer correlation_id when the user begins the transfer journey by selecting the source account (with current transfer type). Keep it until the transfer succeeds, fails definitively, is cancelled/abandoned, or a new transfer journey begins. | Transfer.tsx / journey helper | OBS-001 | Recipient lookup, review, payment submission and final result all carry the same transfer correlation_id. A second transfer in the same session gets a different correlation_id. | Run two transfers in one login session; verify same session_id but different transfer correlation IDs. | Not Started | Journey starts on source-account selection, per agreed design.
UI-004 | React Instrumentation | React | High | As backend services, we need business and session context on API requests without duplicating code in every page. | Enhance shared apiClient to inject X-Correlation-ID and X-Session-ID when supplied by caller/context; keep Authorization handling centralized. | src/api/apiClient.ts | UI-001, UI-002, UI-003 | Authenticated requests can carry session and correlation headers; login can carry correlation_id without JWT; existing idempotency header still works. | Browser Network tab confirms headers for login, recipient lookup and payment. | Not Started | Do not auto-add a stale correlation ID to unrelated requests.
UI-005 | React Instrumentation | React | High | As engineering, I need browser spans and API spans so React activity can be connected to FastAPI traces. | Install/configure browser OpenTelemetry tracing and W3C trace-context propagation for API calls. | src/telemetry/* / main.tsx | OBS-001, UI-004 | React emits spans; outbound API calls include traceparent; FastAPI continues the distributed trace rather than creating an unrelated root trace. | Open one API trace in Tempo and confirm browser -> FastAPI parent/child relationship. | Not Started | Keep instrumentation minimal and understandable.
UI-006 | React Instrumentation | React | Medium | As engineering, I need browser performance visibility without excessive telemetry. | Capture page/navigation timing, API request duration, and uncaught JavaScript errors using low-cardinality attributes. | src/telemetry/* | UI-005 | Metrics exist for page load/navigation duration, API duration and JS error count; no URL query values, account IDs or correlation IDs are metric labels. | Generate a controlled JS error in dev and verify counter; inspect labels. | Not Started
UI-007 | React Instrumentation | React | Medium | As support, I need a small number of meaningful frontend journey events. | Emit only high-value frontend events/spans: journey.started, journey.completed, journey.failed, recipient.verification.failed where applicable. | Login.tsx / Transfer.tsx / telemetry helper | UI-005 | Successful flows do not create noisy click/field-change logs; failed flows contain correlation_id, trace context, journey type/stage and safe error category only. | Complete success and failure flows; compare event volume. | Not Started
UI-008 | React Instrumentation | React | High | As security, I need browser telemetry scrubbed before export. | Add telemetry attribute filtering/sanitization and an explicit denylist for sensitive fields. | src/telemetry/sanitize.ts | OBS-001, UI-005 | No JWT, username, password, customer profile data, account identifiers, recipient label, amount, request/response bodies, or query-string secrets appear in exported telemetry. | Search Loki/Tempo for known synthetic PII values and confirm zero matches. | Not Started
API-001 | FastAPI Correlation | FastAPI | High | As support, I need FastAPI to accept and preserve the UI correlation ID. | Add correlation middleware: read X-Correlation-ID, validate format/length, generate one if missing, place it in request context, and return it in response header. | app/main.py / middleware module | OBS-001, UI-004 | Every request has exactly one valid correlation_id in backend context; UI-provided ID is preserved; missing/invalid ID is safely replaced. | Call API with and without header; verify response and logs. | Not Started | Never trust arbitrary unbounded header values.
API-002 | FastAPI Correlation | FastAPI | Medium | As operations, I need session grouping without customer PII. | Read X-Session-ID into request context for telemetry only; validate format/length; never use it for authentication or authorization. | middleware / request context | UI-001, API-001 | session_id is available to telemetry and absent from business authorization decisions. | Tamper with session_id and verify authorization remains based solely on JWT. | Not Started
API-003 | FastAPI Tracing | FastAPI | High | As engineering, I need W3C trace context continued from React through FastAPI. | Verify/adjust FastAPI OpenTelemetry instrumentation and propagator configuration; preserve existing backend tracing. | telemetry.py / app startup | UI-005 | Inbound traceparent produces a continued trace; backend spans share the same trace_id as the browser request trace. | Tempo trace proves React -> FastAPI continuity. | Not Started
API-004 | FastAPI Business Spans | FastAPI | High | As support, I need important transfer stages visible without tracing every line of code. | Add manual spans around critical transfer phases: account validation, balance validation, payment persistence/commit; recipient verification gets its own meaningful span. | payments.py / accounts.py | API-001, API-003 | Trace contains meaningful high-level spans; no raw SQL, request body, amount, account/customer identifiers, or PII attributes. | Successful transfer trace shows all critical stages in order. | Not Started | Automatic lower-level DB spans may exist, but manual spans remain the primary story.
API-005 | FastAPI Logs | FastAPI | High | As support, I need failure-oriented structured logs tied to the same journey. | Standardize structured logs with correlation_id, trace_id/span_id when available, journey.type, journey.stage, outcome/failure.category; minimize success logs. | telemetry/logging helper + routes | API-001, API-003 | Logs for failures can be retrieved by correlation_id; successful requests do not create bulky per-step logs. | Trigger recipient-not-found and insufficient-funds cases; query Loki by correlation_id. | Not Started
API-006 | FastAPI Metrics | FastAPI | High | As business and operations, I need trendable counters and latency metrics. | Add counters/histograms for login attempts/success/failure, transfer attempts/success/failure, recipient verification failure, API duration and payment duration. | telemetry.py / auth.py / payments.py / accounts.py | OBS-002, API-003 | Metrics expose only low-cardinality labels such as journey, outcome, failure_type, route template and status class. correlation_id/trace_id/customer/payment/account are not metric labels. | Prometheus query confirms expected counters and bounded label values. | Not Started
API-007 | FastAPI Errors | FastAPI | High | As operations, I need failures categorized consistently. | Map expected failures to safe categories: auth, validation, not_found, insufficient_funds, database, network/internal; attach category to logs/spans/metrics without exposing raw exception data. | shared error helper / routes | API-005, API-006 | Grafana can group failures by category; raw stack/SQL/customer data is not exported to normal telemetry. | Exercise each test failure and inspect telemetry. | Not Started
DB-001 | Database Tracing | Database | High | As engineering, I need to see where database time is spent without storing SQL text or parameters. | Enable safe PostgreSQL/psycopg tracing or manual DB spans; configure suppression/sanitization of statement text and parameters. | DB instrumentation configuration | API-003 | Tempo shows DB operation spans/duration; no SQL text, SQL bind values, account numbers, customer data or transfer amount are present. | Search trace attributes for SQL/request data; confirm absent. | Not Started | Correlation ID is observable in trace/log context, not persisted into banking tables.
DB-002 | Database Tracing | Database | High | As support, I need the payment database transaction boundary visible. | Create/verify one high-level span covering atomic payment persistence and commit/rollback outcome. | payments.py DB transaction block | API-004, DB-001 | Successful payment shows DB commit stage; failed DB transaction shows failure/rollback outcome without exposing SQL details. | Run success and forced rollback test; compare traces. | Not Started
DB-003 | Database Validation | Database | Medium | As QA, I need reproducible database scenarios to validate observability. | Maintain SQL validation scripts/queries for success, insufficient funds, cross-customer transfer, and integrity checks using synthetic data only. | scripts/sql/observability_validation.sql | Existing synthetic banking DB | Validation script is read-only except explicitly documented synthetic setup; it can verify resulting payment/transaction integrity for observability tests. | Run against banking_lab and confirm expected records/counts. | Not Started
DB-004 | Database Governance | Database | High | As architecture, I want observability separated from transactional storage. | Confirm no new observability log/trace tables or correlation columns are added to core banking tables unless a future audit requirement explicitly demands persistence. | Schema review | OBS-001 | Banking schema remains business-focused; telemetry stays in Loki/Tempo/Prometheus. | Schema diff before/after implementation shows no telemetry-only persistence. | Not Started
OBS-003 | Telemetry Pipeline | Alloy/Grafana | High | As platform engineering, I need React and FastAPI telemetry to use the existing Alloy path. | Configure Alloy receivers/exporters for browser/backend OTLP while preserving existing Loki/Tempo/Prometheus flow. | Alloy config / compose.observability.yaml | UI-005, API-003 | Alloy receives frontend/backend telemetry and forwards traces to Tempo, metrics to Prometheus, logs to Loki; existing backend dashboards continue to work. | Check Alloy health and backend ingestion after config change. | Not Started
OBS-004 | Telemetry Pipeline | Alloy/Grafana | High | As security, I need a second protection layer against sensitive telemetry. | Add Alloy-side filtering/drop rules for prohibited attributes/headers where practical. | Alloy config | OBS-001, OBS-003 | Known prohibited fields are dropped before storage even if application instrumentation accidentally adds them. | Inject controlled forbidden test attribute in dev; verify it is absent downstream. | Not Started | Defense in depth; app-side sanitization remains required.
OBS-005 | Telemetry Pipeline | Alloy/Grafana | Medium | As engineering, I need reliable trace-log correlation. | Ensure logs include trace_id/span_id and correlation_id; configure Grafana/Tempo/Loki links so a trace can jump to related logs and vice versa. | Alloy/Grafana data source configuration | API-005, OBS-003 | From Tempo trace, operator can open related Loki logs; from a correlation ID search, operator can identify related trace IDs. | Perform one failed transfer and navigate both directions. | Not Started
OBS-006 | Telemetry Pipeline | Alloy/Grafana | Medium | As engineering, I need metrics-to-trace investigation where supported. | Configure exemplars/trace linkage for latency metrics where supported by the current local stack. | Prometheus/Tempo/Grafana config | API-006, OBS-003 | At least one latency metric can link from an exemplar to a representative trace, or limitation is documented if local stack does not support it. | Generate transfer traffic and test metric -> trace drill-down. | Not Started
GRAF-001 | Dashboards | Alloy/Grafana | High | As an executive/business stakeholder, I need a concise journey health dashboard. | Build Business Journey Overview dashboard: login attempts/success/failure, transfer attempts/success/failure, success rate, average duration, daily/weekly/monthly trends. | Grafana dashboard JSON provisioning | API-006, OBS-003 | Dashboard answers volume, success rate and trend questions without exposing technical IDs or customer data; selectable time range supports daily/monthly/yearly views. | Validate panels against known synthetic test counts. | Not Started | No correlation IDs on executive dashboard.
GRAF-002 | Dashboards | Alloy/Grafana | High | As operations/support, I need to find and investigate failed customer journeys quickly. | Build Support Journey Investigation dashboard: failures over time, journey/failure stage breakdown, recent failures, correlation ID search, links to logs/traces. | Grafana dashboard JSON provisioning | API-005, API-006, OBS-005 | Given a correlation_id, support can retrieve related failure logs and trace(s) without customer PII; recent failure panels show safe fields only. | Trigger failed login, recipient lookup and transfer; investigate each from dashboard. | Not Started
GRAF-003 | Dashboards | Alloy/Grafana | High | As engineering/operations, I need technical performance and dependency health. | Build Engineering Observability dashboard: frontend API duration, page/navigation performance, JS errors, FastAPI latency/error rate, payment duration, DB span duration, slow traces. | Grafana dashboard JSON provisioning | UI-006, API-006, DB-001 | Dashboard shows frontend/backend/DB latency and error trends; panels can drill into traces/logs; no sensitive labels. | Generate normal + slow/error scenarios and verify panels react. | Not Started
GRAF-004 | Dashboards | Alloy/Grafana | Medium | As operators, I need dashboard variables that are useful but safe. | Add variables for environment, service, journey type, outcome/failure category and time range; avoid customer/correlation IDs as broad metric variables. | Grafana dashboard JSON provisioning | GRAF-001, GRAF-002, GRAF-003 | Variables use bounded values and do not create high-cardinality metric queries. | Inspect variable query results and dashboard performance. | Not Started
E2E-001 | End-to-End Validation | Cross-cutting | High | As support, I need one correlation ID to retrieve a complete transfer story. | Execute external-recipient transfer: source selection -> recipient verification -> review -> payment -> DB commit; capture correlation ID and prove visibility across UI/API/DB-related telemetry. | React + FastAPI + Tempo + Loki | UI-003, API-004, DB-002, OBS-005 | Same correlation_id is visible across all relevant events/logs/spans; recipient lookup and payment may have different trace_ids but belong to the same correlation_id. | Document screenshots/query evidence for one successful transfer. | Not Started
E2E-002 | End-to-End Validation | Cross-cutting | High | As support, I need failures to identify the exact stage. | Run failure scenarios: invalid login, recipient not found, insufficient funds, and controlled backend/DB failure. | Full stack | API-007, GRAF-002 | Each failure appears with journey type, correlation_id where applicable, failure stage/category, safe message, trace/log drill-down; no sensitive data leaks. | Validate each scenario in Support dashboard. | Not Started
E2E-003 | End-to-End Validation | Cross-cutting | High | As security, I need proof that monitoring stores no PII/NPI/secrets. | Run automated/manual sensitive-data audit across Loki/Tempo/Prometheus for known synthetic usernames, names, emails, phones, DOBs, addresses, account numbers, JWT fragments, recipient labels and transfer amount. | Validation script / Grafana queries | UI-008, OBS-004, DB-001 | Zero prohibited matches. Any unavoidable framework metadata is documented and assessed. | Run audit after success/failure traffic generation. | Not Started
E2E-004 | End-to-End Validation | Cross-cutting | Medium | As platform engineering, I need to understand observability overhead. | Measure baseline vs instrumented API/frontend latency and telemetry volume under a small repeatable load. | React/FastAPI/Alloy | OBS-003 | Overhead is measured and documented; no material functional regression; telemetry volume is understandable enough to estimate future scaling. | Run same synthetic workflow before/after instrumentation and compare. | Not Started
E2E-005 | Operational Readiness | Cross-cutting | Medium | As operations, I need a short investigation runbook. | Create runbook: start from alert/dashboard -> correlation ID -> metrics -> trace -> span -> logs -> service/DB stage; include common queries and privacy rules. | README / docs | GRAF-001, GRAF-002, GRAF-003 | A new operator can investigate a failed transfer using the runbook without opening source code or querying business tables. | Dry-run investigation using only the runbook. | Not Started
E2E-006 | Operational Readiness | Cross-cutting | High | As the project owner, I need a final Definition of Done before calling the observability POC complete. | Perform final regression: login, accounts, profile, internal transfer, external transfer, transaction history, dashboard refresh, all three Grafana dashboards, privacy audit and correlation drill-down. | Full solution | All prior items | Existing banking functionality remains working; observability requirements are met; dashboards are provisioned/reproducible; no PII/NPI leakage; documentation is current. | Signed-off checklist. | Not Started

## Telemetry Contract
Telemetry Contract - IDs, Signals, Safe Attributes and Data Handling
Concept | Purpose | Lifecycle | Where Used | Allowed Examples | Never Put Here
session_id | Groups activity from one authenticated browser session without using customer identity. | Created after successful login; cleared on logout/browser session end. | React headers, safe telemetry attributes, support analysis. | Random opaque UUID. | customer_id, username, email, account number, JWT
correlation_id | Groups all technical requests belonging to one business activity/journey. | New per login attempt and per transfer journey. Transfer begins on source-account selection and remains through recipient verification/payment result. | X-Correlation-ID header, logs, spans, support search. | Random UUID. | As a metric label; customer/account/payment identity
trace_id | OpenTelemetry identifier for one distributed technical trace. | Generated/propagated by OpenTelemetry per technical request trace. | Tempo, trace/log links, exemplars. | OTel-generated trace ID. | Business identity replacement
span_id | Identifies one operation inside a trace. | Generated by OpenTelemetry per span. | Tempo, structured logs. | OTel-generated span ID. | Customer or transaction identifiers
Approved High-Level Journey Stages
Journey | Stage | Signal Preference | Notes
login | login.started | span/event + counter | No username/password.
login | login.completed | span/event + success counter/duration | No customer identity.
login | login.failed | log/span event + failure counter | Safe failure category only.
transfer | transfer.started | span/event + counter | Create correlation_id at source-account selection.
transfer | recipient.verification | span; log only on failure | Same transfer correlation_id.
transfer | transfer.reviewed | span/event | No amount/account attributes.
transfer | payment.submitted | span/event | Preserve idempotency behavior.
transfer | payment.validation | backend span; log on failure | Account/balance validation without values.
transfer | payment.database | backend/DB span; log on failure | No SQL text/parameters.
transfer | payment.completed | span/event + success counter/duration | Final journey outcome.
transfer | payment.failed | log/span event + failure counter | Include safe failure stage/category.
Sensitive Data Policy
Allowed / Safe | Conditional / Aggregate Only | Prohibited
service.name, environment, route template, HTTP status class | Transfer amount only as future aggregate business metric if explicitly approved | Username / password
journey.type, journey.stage, outcome | Opaque session_id | JWT / authorization header
safe failure.category | Correlation ID in logs/traces only | Customer ID / name / email / phone / DOB / address
trace_id/span_id in logs/traces | Payment ID only if later explicitly approved for support use | Full or masked account number
duration/counts | Internal synthetic-only test markers | Recipient name / label
HTTP method / route template | No individual transfer value in logs/traces | Raw SQL / SQL parameters / request or response bodies

## Dashboard Plan
Grafana Dashboard Solution Plan
Dashboard | Audience | Primary Questions | Core Panels | Primary Signal | Drill-down | Privacy Guardrail | Acceptance
Business Journey Overview | Executives / business | How many logins/transfers? Success rate? Are trends improving? Are journeys getting slower? | Login attempts/success/failure; transfer attempts/success/failure; success rate; avg duration; daily/weekly/monthly trend; optional yearly trend. | Metrics | From trend panel to Support dashboard/time window. | No correlation/customer/account identifiers. | Counts match synthetic tests and trends respond to time-range changes.
Support Journey Investigation | Support / operations | What failed? At which stage? Can I retrieve all related evidence using one correlation ID? | Failures over time; failure stage/category; recent failures; correlation ID search; related logs; trace links. | Logs + traces + metrics | Correlation ID -> Loki logs -> Tempo trace(s). | Safe fields only; no PII/NPI, amount, account data. | A failed login/recipient lookup/transfer can be investigated without source code or DB queries.
Engineering Observability | Engineering / SRE / platform | Where is latency? Is frontend/API/DB unhealthy? Are JS/API/database errors increasing? | Frontend API duration; page/navigation duration; JS errors; FastAPI latency/error rate; payment latency; DB span duration; slow traces. | Metrics + traces | Metric -> exemplar/trace (if supported) -> spans -> logs. | No high-cardinality business IDs as metric labels. | Normal and induced slow/error scenarios visibly change relevant panels.
Recommended Dashboard Variables
Variable | Use | Do Not Use
Time range | Daily, weekly, monthly, yearly analysis | N/A
Environment | local/dev/test/prod separation | Customer-specific values
Service | React/FastAPI/etc. | Correlation ID as a metric variable
Journey type | login / transfer | Account/payment/customer IDs
Outcome / failure category | success/failure and safe grouped reason | Raw exception text

## Milestones & DoD
Implementation Sequence, Milestones and Definition of Done
Milestone | Scope | Entry Criteria | Exit / Acceptance | Key Demo | Status | Notes
M1 - Telemetry Contract | IDs, stages, safe attributes, privacy rules | Current app/backend observability baseline working | Contract frozen; naming/PII rules approved | Explain session/correlation/trace/span model | Not Started
M2 - React Journey Context | session_id, correlation_id, shared headers, browser OTel | M1 | Login and transfer correlation IDs generated/propagated; no sensitive telemetry | Two transfers in one session: same session_id, different correlation IDs | Not Started
M3 - FastAPI Correlation & Tracing | middleware, trace propagation, business spans, structured logs/metrics | M2 | React -> FastAPI trace continuity; safe high-level transfer spans; bounded metrics | Follow recipient lookup and payment through backend | Not Started
M4 - DB Visibility | safe DB spans, transaction boundary, validation scripts | M3 | DB duration/commit/rollback visible with no SQL text/params | Show payment DB stage in trace | Not Started
M5 - Alloy Pipeline Hardening | frontend/backend ingestion, filtering, links | M2-M4 | All signals arrive in correct backends; sensitive attribute filters active | Trace <-> logs navigation | Not Started
M6 - Grafana Dashboards | Business, Support, Engineering dashboards | M5 | Dashboards answer audience questions and support time trends/drill-down | Executive trend + failed transfer investigation + slow trace | Not Started
M7 - End-to-End Sign-off | success/failure regression, privacy audit, overhead, runbook | M1-M6 | Full functional regression passes; no PII/NPI leaks; dashboards reproducible; runbook complete | One correlation ID from UI journey to API/DB telemetry and dashboards | Not Started
Final Definition of Done
Check | Acceptance
Functional regression | Login, Accounts, Profile, internal transfer, external transfer, transaction history and Dashboard refresh still work.
Journey correlation | A transfer correlation_id covers source selection, recipient verification, review/payment and final result; a second transfer gets a new ID.
Distributed tracing | Browser trace context continues into FastAPI; DB-related stages appear in trace.
Logs | Failures are searchable by correlation_id and contain safe stage/category information only.
Metrics | Login/transfer volume, success/failure and duration metrics are available with bounded labels.
Privacy | No JWT, credentials, PII/NPI, account identifiers, recipient label, raw SQL/params, request/response bodies or individual transfer amount in logs/traces/metric labels.
Dashboards | Business, Support and Engineering Grafana dashboards are provisioned and validated.
Trends | Time-range queries support daily/monthly/yearly decision-making where sufficient data exists.
Investigation | Support can start from dashboard/correlation_id and reach related trace(s) and logs.
Reproducibility | All config/dashboard changes are source-controlled/provisioned rather than manual-only.

## Summary
Happy Wallet Bank - Observability POC Delivery Summary
Design Principle | Decision | Tracker KPI | Value
Transfer journey start | Create correlation_id when source account is selected for the chosen transfer type. | Total Tasks | 35
Journey identity | New correlation_id per business activity; login and each transfer are separate. | High Priority | 26
Session grouping | Opaque session_id per authenticated browser session; no customer identity in telemetry. | React Tasks | 8
Technical tracing | OpenTelemetry trace_id per distributed technical trace; span_id per operation. | FastAPI Tasks | 7
Telemetry routing | React/FastAPI -> Alloy -> Tempo/Loki/Prometheus -> Grafana. | Dashboard Tasks | 4
|  | Status | Count
|  | Not Started | 35
|  | In Progress | 0
|  | Blocked | 0
|  | Done | 0